## Slide 1
AOPC 22 Actions
3 teleconferences during the year where progress on actions was discussed.
23 actions from AOPC 22
  13 actions closed
    Task teams (GUAN,GSRN,Radar,Lightning)
    Work with WMO on RRR and OSCAR and on metadata
    Work with Copernicus
    Work on ECV requirements
  9 in progress – 5 are going to be addressed at this meeting
  1 no progress

## Slide 2
22/2 | Open data policy: Copernicus to request support from GCOS on national data availability and associated metadata. Involve WIGOS. | Peter Thorne | October 2017 | Still open. We would still like secretariat to engage national focal points to enquire around data availability and get those willing to submit to the NCEI and Copernicus archival effort. What is required is that we draft a letter that gets transmitted to FPs (not PRs!) asking for consideration of submission of national holdings of surface met obs and metadata to the effort.
22/4 | IP actions: Identify experts on the way forward for IP actions postponed for future | AOPC | January 2018 | At next AOPC identify other experts (included on agenda)
OPEN ACTIONS from AOPC22
22/8 | Cloud and water vapour: Ken Holmlund to discuss with Carolin Richter and Stephen Briggs how to best bring up to the space agencies the requirement for lidar type of mission . Possibly produce an AOPC position paper. | Ken Holmlund | June 2017 | Ken has asked for an amendment for WIGOS2040 to better capture this requirement. Discuss whether a position paper is needed

## Slide 3
22/11 | IP requirements for GHG: Unify the IP requirements for GHG. Jim Butler to start working at the GGMT in August | James Butler, Greg Carmichael | AOPC23 | Discuss Jim’s update at AOPC during session on ECV requirements (included on agenda)
22/12 | Metadata standards: Facilitate contact with regard to the potential for the Copernicus service to use OSCAR (WIGOS). OSCAR only uses pub 9 as id, but Copernicus needs a larger set of station ids. | GCOS Secretariat and Peter Thorne | June 2017 | We have a discussion document that now needs transmission to Copernicus. Peter is awaiting sign off from WIGOS colleagues. Caterina needs to get Steve or Maxx to approve and the he can move this into C3S
22/13 | Metadata standards: AOPC to communicate to the other panels the decision to use WIGOS metadata standards and follow up. Set up a joint group to consider an extension for climate records standards that can build up on work already done by the climate CEOS CGMS JWG. | GCOS Secretariat | GCOS SC | For the atmosphere use the WIGOS metadata standards. However, in order to guarantee a consistent approach across the panels, each panel is invited to appoint a member and form a joint working group on metadata standards. (Action SC 25/16)

## Slide 4
22/14 | Review of ECV Observation Networks: Contact Dick Dee in September to ask who was awarded the EQC contract and initiate a discussion, which includes details on how the work will move forward | GCOS Secretariat | Sept | Contract started in Nov 2017. Peter is the WP lead for surface ECVs EQC. It shall consider adequacy against GCOS requirements, maturity (against the more sane CORE-CLIMX criteria), aspects of fitness for purpose and assessment of quality using a modified version of the ESMVal tool. Peter suggests inviting a talk on this at next AOPC (he could give the talk if GCOS is unable to cover invitation costs). At that point there will be an example of the output and thus be in a position to consider whether this partly or wholly meets GCOS needs
22/16 | RRR and OSCAR: Assistance in updating content of OSCAR/requirements for AA Climate Monitoring. | GCOS Secretariat |  | Included on agenda

## Slide 5
22/23 | CATCOS: Report back to AOPC on performance of 5 CATCOS stations and use of support funds. | GCOS Network manager |  | Draft agreement between WMO and the Swiss institutes who manage CATCOS has been agreed, and is in the process of being signed. Thus the support from GCOS will cover the period 2018 to 2020. Tim to report back to the next AOPC on the performance of the CATCOS stations.
NO PROGRESS
22/20 | Parallel observations collection and analysis effort: GCOS sec to discuss with the other panels requests 1. and 2. from text above (Section 11.5 of AOPC 22 report). | GCOS Secretariat | GCOS SC | No decision at the SC was reached about the systematic collection of parallel measurements.