## Slide 1
IP AOPC Actions
40 actions
Surface:
In progress: A1-A2-A3-A4-A5-A6-A7-A8-A9-A11
A1, A11 (GSN and BSRN) monitored by Tim
A2-A6-A7-A9 (Peter, Imke, Liz) – related to work with C3S and to observations over ocean
A5 - Transition to Bufr GUAN TT
A3 and A8 (Radar TT): need responsible AOPC member
No Progress: A10, A12

## Slide 2
Action A3 | International exchange of SYNOP and CLIMAT reports |  |  | Status
Explanation | Obtain further progress in the systematic international exchange of both hourly SYNOP reports and daily and monthly CLIMAT reports from all stations |  |  | 
Benefit | Enhanced holdings data archives | Time Frame | Continuous, with significant improvement in receipt of RBSN synoptic and CLIMAT data by 2019 | 
Who | NMHSs, regional centres in coordination/cooperation with WMO CBS, and with advice from AOPC | Performance Indicator | Data archive statistics at data centres | 
Background | This has to be considered not only a work of monitoring, but where gaps are found, it requires an action. | Responsible within AOPC: GSNMC, Andreas Becker |  | 
 |  | Timeframe/ deliverables: Annual report and presentation to AOPC |  | 
20th June | Sent email to Andreas |  |  | 
20th Sep. | None – send an email to Andreas asking for input (Secretariat) |  |  | 
9th Jan 2018 | Email sent . Update received from Andreas. Software design and concept Document addressing this request has been procured and completed. The new Web Page will Feature the following capabilities: - digesting BUFR - Monitoring and visualization arrivals at deadlines that can be customized - increased scope of stations monitored to Include all RBCN stations Three Prototypes have been implemented. If requested my colleague Peter Finger can provide you with Illustrations. Moreover Christel Lefevbre can provide more Detail as she has Governed the Software procurement. In case that the Financial resources can be Secured the GSNMC Web Page Upgrade shall be implemented this year. |  |  | 

## Slide 3
Action A8 | Provide precipitation data to the Global Precipitation Climatology Centre |  |  | Status
Explanation | Submit all precipitation data from national networks to the Global Precipitation Climatology Centre at the Deutscher Wetterdienst |  |  | 
Benefit | Improved estimates of extremes and trends, enhanced spatial and temporal detail that address mitigation and adaptation requirements | Time Frame | Ongoing | 
Who | NMHSs with coordination through the WMO CCl and the GFCS. | Performance Indicator | Percentage of nations providing all their holdings of precipitation data to international data centres. | 
Background | Getting also radar data into precipitation data; associated with Task Team for radar data for climatology (Elena) | Responsible within AOPC: Andreas Becker and Leader of the task team for radar for climatology |  | 
 |  | Timeframe/ deliverables: Useful to supply precipitation data to C3S/NCEI |  | 
20th June | Part of the radar task team work |  |  | 
20th Sep. | Ongoing work of radar TT. |  |  | 

## Slide 4
Action A10 | Incorporating national sunshine records into data centres |  |  | Status
Explanation | National sunshine records should be incorporated into International Data Centres |  |  | 
Benefit | Better description of surface radiation fields | Time Frame | Implement in next 2 years | 
Who | NMHS | Performance Indicator | Performance indicator Sunshine record archive established in international data centres and in analysis centres by 2018 | 
Background | National sunshine records into Data Centres | Responsible within AOPC: |  | 
 |  | Timeframe/ deliverables: Future |  | 
20th June |  |  |  | 
20th Sep. | Both for A10 and A12: Many data are in private hands and risk to be lost. We need to encourage them to make the data available. |  |  | 

## Slide 5
Action A12 | Surface radiation data to the World Radiaiton Data Centre |  |  | Status
Explanation | Submit surface radiation data with quality indicators from national networks to the WRDC; expand deployment of surface radiation measurements over ocean |  |  | 
Benefit | Expand central archive; data crucial to constrain global radiation budgets and for satellite product validation; more data over ocean would fill an existing gap. | Time Frame |  | 
Who | NMHS and others, in collaboration with WRDC | Performance Indicator | Data availability in WRDC | 
Background |  | Responsible within AOPC: |  | 
 |  | Timeframe/ deliverables: Future |  | 
20th June | Future |  |  | 
20th Sep. | Both for A10 and A12: Many data are in private hands and risk to be lost. We need to encourage them to make the data available. |  |  | 

## Slide 6
Upper-air:
In progress: A13-A14-A17 - GUAN Task Team
A15 GRUAN (Ruud)
A16-A19-A21-A25-A27 Satellite (Joerg)
A22- Invited F. Madonna
A23- Do we need a special presentation at GRUAN?
A24: Radar TT
A26
A29: Lightning TT
No progress: A18, A20 A28

## Slide 7
Action A18 | Hyperspectral radiances reprocessing |  |  | Status
Explanation | Continue reprocessing of AMVs derived from geostationary satellite imagery in a coordinated manner across agencies |  |  | 
Benefit | Consistent time series of AMVs for monitoring and reanalyses, improved CDRs computed from the FCDRs | Time Frame | Ongoing | 
Who | Space agencies | Performance Indicator | Reprocessed FCDRs available for upper-air winds | 
Background | This action is about reprocessing level 1 radiances. In process. There is a need to involve American CRIS and AIRS experts to share experience on how to produce a consistent record and to ensure consistency with IASI. | Responsible within AOPC: Ken Holmlund |  | 
 |  | Timeframe/ deliverables: |  | 
20th June | not followed up yet, no progess |  |  | 
20th Sep. | No progress. |  |  | 

## Slide 8
Action A20 | Increase the coverage of aircraft observations |  |  | Status
Explanation | Further expand the coverage provided by AMDAR, especially over poorly observed regions such as Africa and South America |  |  | 
Benefit | Improved coverage of upper-air wind for monitoring and reanalysis | Time Frame | Ongoing | 
Who | NMHSs, WIGOS, RAs I and III. | Performance Indicator | Data available in recognized archives | 
Background | Future | Responsible within AOPC: |  | 
 |  | Timeframe/ deliverables: |  | 
20th June |  |  |  | 
20th Sep. |  |  |  | 

## Slide 9
Action A28 | In-situ Profile and Radiation |  |  | Status
Explanation | To understand the vertical profile of radiation requires development and deployment of technologies to measure in-situ profiles. |  |  | 
Benefit | Understanding of 3D radiation field, model validation, better understanding of radiosondes | Time Frame | Ongoing | 
Who | NMHSs, National measurements institutes, HMEI | Performance Indicator | Data availability in NMHSs archives | 
Background | Future | Responsible within AOPC: |  | 
 |  | Timeframe/ deliverables: |  | 
20th June |  |  |  | 
20th Sep. |  |  |  | 
Jan 2018 | This was work of Meteo Swiss (Payerne) site by a staff member no longer employed. Would suggest that Secretariat follow up with Bertrand Calpini to ascertain status of this work. |  |  | 

## Slide 10
Composition
In progress:
A30 satellite
A31 (Peter and Joerg on Thursday)
A34 (Dale)
A40
No progress:
A32-A33-A36 (No responsible within AOPC)
A35-A37-A38-A39

## Slide 11
Action A32 | Fundamental Climate Data Records and Climate Data Records for greenhouse gases and aerosols ECVs |  |  | Status
Explanation | Extend and refine the satellite data records (FCDRs and CDRs) for GHG and aerosol ECVs |  |  | 
Benefit | Improved record of GHG concentrations | Time Frame | Ongoing | 
Who | Space agencies | Performance Indicator | Availability of updated FCDRs and CDRs for GHGs and aerosols | 
Background |  | Responsible within AOPC: |  | 
 |  | Timeframe/ deliverables: |  | 
20th June | No progress |  |  | 
20th Sep. | Not started yet |  |  | 

## Slide 12
Action A33 | Maintain WMO GAW CO2 and CH4 monitoring networks |  |  | Status
Explanation | Maintain and enhance the WMO GAW Global Atmospheric CO2 and CH4 monitoring networks as major contributions to the GCOS Comprehensive Networks for CO2 and CH4. Advance the measurement of isotopic forms of CO2 and CH4 and of appropriate tracers to separate human from natural influences on the CO2 and CH4 budgets |  |  | 
Benefit | A well-maintained, ground-based and in situ network provides the basis for understanding trends and distributions of GHGs. | Time Frame | Ongoing | 
Who | National Environmental Services, NMHSs, research agencies, and space agencies under the guidance of WMO GAW and its Scientific Advisory Group on Greenhouse Gases | Performance Indicator | Data flow to archive and analysis centres | 
Background | Generally ongoing, advance the measurement of isotopic forms of CO2 and CH4, and of appropriate tracers, to separate human from natural influences on the CO2 and CH4 budgets | Responsible within AOPC: Jim Butler |  | 
 |  | Timeframe/ deliverables: Interim report for AOPC-23 2018 on data flow |  | 
20th June | meeting in September, will bring up satellite issues, with Greg how to identify, important step In measurement guidelines |  |  | 
20th Sep. | Greg will check about the meeting with Jim and send an update |  |  | 

## Slide 13
Action A36 | N2O, halocarbon and SF6 networks/measurements |  |  | Status
Explanation | Maintain networks for N2O, halocarbon and SF6 measurements |  |  | 
Benefit | Informs the parties to the Montreal Protocol, provides records of long-lived, non-CO2 GHGs and offers potential tracers for attribution of CO2 emissions | Time Frame | Ongoing | 
Who | National research agencies, national environmental services, NMHSs, through WMO GAW | Performance Indicator | Data flow to archive and analysis centres | 
Background | Future | Responsible within AOPC: |  | 
 |  | Timeframe/ deliverables: |  | 
20th June |  |  |  | 
20th Sep. |  |  |  | 

## Slide 14
Possible break out groups
Surface: Imke, Liz, Phil, Rainer, (Peter)
Upper Air: Ken, Shinya, Ruud, Tim, Peng
Composition: Greg, Dale, Olga, Zhanqing, Peng