## Slide 1
ECV Requirements
Simon Eggleston
How should we define ECV and their requirements?

## Slide 2: Essential Climate Variables (ECV)
 | ACTION | WHO | When
2 | Participate in review of WCRP Strategic Plan. | All | June 2018
3 | Provide feedback on GCSO Indicators how well these are presented. | All | 
4 | Make list of ECV stewards and action rapporteurs public to allow credit for their efforts | GCOS Sec | End April
5 | ECV Stewards to fill out ECV requirements for each product on the TOPC forum | ECV Stewards | June 2018
6 | Produce a consolidated proposal, after consulting other panels, for how to specify requirements, definitions, with 3 values if appropriate | GCOS Sec | For SC
7 | Prepare for wider review of refined ECV Products requirements, based on forum discussions for consideration by panel | GCOS Sec | TOPC21
8 | Liaise with ocean panel on what they want/need in coastal areas. | Simon | For SC
9 | Each ECV steward to identify gaps in monitoring guidance if appropriate (Action T4). | ECV Stewards | Dec 2018
10 | Action rapporteurs to continue to update progress on actions, on-going action. First version by June 2018, then to report by TOPC 21 on important actions. |  | June 2018 & report to TOPC21
11 | Represent TOPC in discussions on metadata with other GCOS science panels | Nadine | On-going
12 | Secretariat to prepare and upload factsheets to TOPC forum | GCOS Sec | Mid-April

## Slide 3: Essential Climate Variables (ECV)
 | ACTION | WHO | When
13 | ECV Stewards to check and update factsheets | ECV Stewards | End May
14 | Members to identify additional experts for ECV, not covered by panel, as indicated in TOPC forum | Panel members | End April
15 | Contact Han Dolman if he could be rapporteur for GHG fluxes | GCOS Sec | End April
16 | Contact Huilin Li to confirm she is rapporteur and ECV Steward | GCOS Sec | End April
17 | Contact Darren Ghent to confirm he is rapporteur and ECV Steward | GCOS Sec | End April
18 | Maintain TOPC link with GCOS Surface Reference Network Task Team. | Nigel | 
19 | Task team on monitoring for adaptation. Draft & Agree ToR, Identify members. Interim report to next SC in October and final report to TOPC21. | Nigel chair | SC and TOPC21
20 | Put potential/proposed ECV climate signals on TOPC forum for discussion and review by the panel | Panel Members | 
21 | Send Space Agencies Response to Implementation Plan to Panel Members | GCOS Sec | After meeting
22 | Arrange telcon for TOPC. 1st in June to assess progress on forum, 2nd in September to prepare for SC and 3rd in January to prepare for joint panel meeting in Morocco, | GCOS Sec and TOPC Chair | June, September, January
23 |  |  | 
24 |  |  | 

## Slide 4
gcos.wmo.int
@gcos_un
thank you